## Sheet1
|  | Types.js |  | Client.js |  |  |  | Dialog
Function | Selector | Handler attached | Handler written | Method to open dialog created | Method to open dialog written | Completion method created | Completion or callback written | js created | jade created | js modified | jade modifed | finished and tested | Can be done solely on project in memory | Notes
Delete Type | #TWdeleteTypeBtn | x | x | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a |  | yes | Validate that it's deletable before opening dialog.
New Type | #TWnewTypeBtn | x | x | x | x | x | x | x | x | x | x | x | yes
Search for Type | #TWsearchTypeBtn | x | x | x | x | x | x | x | x | x | x
Rename method | #methodrename_[index] | x | x | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a |  | yes
Delete method | #methoddelete_[index] | x | x | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a |  | yes | Validate that it's deletable before opening dialog.
Add Method | #TWaddMethodBtn | x | x | x | x | x | x | x | x |  |  |  | yes
Search for Method | #TWsearchMethodBtn | x | x | x | x | x | x | x | x
Add Property | #TWaddPropertyBtn | x | x | x | x | x | x | x | x |  |  |  | yes
Edit Property | #propertyedit_[index] | x | x | n/a | n/a |  |  | n/a | n/a | n/a | n/a |  | yes
Delete Property | #propertydelete_[index] | x | x | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a |  | yes | Validate that it's deletable before opening dialog.
Add Event | #TWaddEventBtn | x | x | x | x | x | x | x | x |  |  |  | yes
Rename Event | #eventrename_[index] | x | x | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a |  | yes
Delete Event | #eventdelete_[index] | x | x | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a |  | yes | Validate that it's deletable before opening dialog.
Delete Confirmation (handles Type, Method, property, Event) | n/a | n/a | n/a | x | x | n/a |  | x | x | x | x |  | yes
Generic Rename (handles Method, Event) | n/a | n/a | n/a | x | x | n/a |  | x | x | x | x |  | yes
work with method in code section | #method_[index] | x | x |  |  |  | Client has: | self.addMethodToType(clMethod) |  |  |  | x | These aren't tested, just written.
[8 empty] | self.addMethodToTyoeFromDB(iMethodId) |  |  |  | x
[8 empty] | self.addPropertyToType(clProperty) |  |  |  | x
Method.js | [7 empty] | self.addEventToType(clEvent) |  |  |  | x
Property.js | [7 empty] | These are called from NewMethod, SearchForMethod, NewProperty and NewEvent dialogs.
Event.js | [6 empty] | Also: | self.deleteType(clType)
[8 empty] | self.deleteMethod(clMethod) |  |  |  |  | see m_functionDeleteDialogHelper in Type.js
self.deleteProperty(clProperty)
self.deleteEvent(clEvent)
These are called from DeleteConfirmDialog.
Note on A3: Gerald Rubin: Uses omnibus delete dialog
Note on A6: Gerald Rubin: Uses omnibus rename dialog
Note on A7: Gerald Rubin: Uses omnibus delete dialog
Note on A10: Gerald Rubin: Dialog is shared with Edit Property
Note on A11: Gerald Rubin: Dialog is shared with New Property
Note on A12: Gerald Rubin: Uses omnibus delete dialog
Note on A14: Gerald Rubin: Uses omnibus rename dialog
Note on A15: Gerald Rubin: Uses omnibus delete dialog

## Sheet2
Type.js#m_functionDeleteDialogHelper is called with parameters
|  | Type | Method | Property | Event
| strType | "type" | "method" | "property" | "event"
| arrayCollection | null | self.data.methods | self.data.properties | self.data.events
| iIndex | -1 | iIndex | iIndex | iIndex
| objectMember | self.data | methodClicked | propertyClicked | eventClicked
Type.js#m_functionRenameDialogHelper is called with parameters (original name is first saved to m_strOriginalName)
The function also has a 3rd parameter (bNew). bNew is set to true in 1 case: in m_functionAddPropertyClick.
|  | Type | Method | Property | Event
| strType | "type" | "method" | "property" | "event"
| objectMember | self.data | methodClicked | propertyClicked | eventClicked